## DAILY_KPI_SNAPSHOT
Date | Entity | Revenue | Cash | Pipeline_Value | Closings_Count | Orders_Count | Occupancy | Alerts | Notes
2026-02-10 | Perpetual | 125000 | 54000 | 2100000 | 2 | 18 |  | All good | Strong day
2026-02-10 | TCSL | 98000 | 43000 | 1750000 | 1 | 12 | 92 | Occupancy stable | On track
2026-02-10 | LLV | 143000 | 67000 | 2540000 | 3 | 0 |  | High revenue | Heavy closing activity

## DEAL_PIPELINE
Deal_Name | Entity | Status | PSA_Date | DD_Deadline | Closing_Date | Deal_Value | Financing_Status | Title_Status | Survey_Status | Seller_Deliverables | Legal_Status | Checklist_Completion_% | Last_Update_Date | Days_Stalled | Owner | Priority | Notes
Oak Street Acquisition | LLV | Under Contract | 2026-02-01 | 2026-02-20 | 2026-03-15 | 4200000 | Pending | In progress | Not started | Partial | Reviewing | 45 | 2026-02-12 | 3 | Nick | High | Waiting on lender package
Maple Apartments | TCSL | Open |  | 2026-03-01 | 2026-04-10 | 3100000 | Not started | Not started | Not started | Pending | Not started | 10 | 2026-02-08 | 6 | Sarah | Medium | Early underwriting
River Bend Portfolio | Perpetual | Closing | 2026-01-15 | 2026-02-05 | 2026-02-25 | 5600000 | Secured | Clear | Complete | Complete | Approved | 90 | 2026-02-11 | 0 | David | High | Ready to close

## TASK_ACCOUNTABILITY_TRACKER
Task_ID | Task | Entity | Category | Owner | Status | Priority | Start_Date | Due_Date | Completion_Date | Days_Overdue | Blocked_By | Related_Deal | Notes
T-001 | Send lender package | LLV | Finance | Nick | In progress | High | 2026-02-05 | 2026-02-14 |  | 0 |  | Oak Street Acquisition | Awaiting final docs
T-002 | Update underwriting | TCSL | Sales | Sarah | Blocked | High | 2026-02-03 | 2026-02-10 |  | 3 | Need rent roll | Maple Apartments | Missing file
T-003 | Close legal review | Perpetual | Legal | David | Not started | Medium | 2026-02-08 | 2026-02-18 |  | 0 |  | River Bend Portfolio | Scheduled with attorney

## WEEKLY_METRICS (TRENDS)
Week | Entity | Revenue | Pipeline | Closings | Occupancy | Cash | Orders | Alerts
2026-W06 | Perpetual | 540000 | 3200000 | 4 |  | 210000 | 65 | None
2026-W06 | TCSL | 410000 | 2750000 | 2 | 91 | 180000 | 52 | Occupancy dip
2026-W06 | LLV | 630000 | 3900000 | 5 |  | 295000 | 0 | Strong closings